## Sheet1
Template: |  | Stakeholder Map
Project: |  | Common Protocol Template
Date: |  | 2017-06-01
Stakeholder Group | Deliverable Optional | Internal or external | What's changing for the stakeholder group? | Level of Change (H, M,L) | Type of Change Optional (People, Process, Tech., Org) | What are the biggest concerns/issues that this stakeholder group may have? | What are the greatest benefits this stakeholder will receive? | What does this stakeholder need? (Training, Communications etc.)
Template owners |  | Internal | template | H | Process, Tech | New template - need to determine how to ensure all the Sponsor's requirements are met within the new template | Streamlined across all TAs | training on how to use the new template and how it may differ form the previous version.
Authors (of protocols, CSRs) |  | Both | template endpoints, libraries | M | Process, Tech | Understanding the new layout and use of the libraries, endpoints, etc. | Efficiency in downstream documents (i.e. CSRs, results reporting) Able to create efficiencies with the defined variables and components for reuse Reduced errors | training on the use of the new template, libraries and new technology components
Medical Writers |  | Both | template, endpoints, libraries | M | Process, Tech | Understanding the new layout and use of the libraries, endpoints, etc. | Efficiency in downstream documents (i.e. CSRs, results reporting) Able to create efficiencies with the defined variables and components for reuse Reduced errors | training on the use of the new template, libraries and new technology components
Publishers/eSubmission formatting specialists |  | Both | template | L | Tech | Understanding the new layout of the libraries, endpoints, etc. | Streamlined across all Therapeutic Areas | Communication as the template is revised
Clinicians |  | Both | template | M | Process | Beocming familiar with the format Understanding how to adapt to the new layout | Efficiencies in review. Clinicians will be able to benefit from the reuse of the common language prepoulated within the template | Communication, training on the layout and use of libararies
Informed Consent authors |  | Internal | template | L | Process | the teams will be working with a new source for multiple components of the ICF | consistancy in the protocol will carry over into the ICF | Communication, training on the format & layout of the new template
Study Mgmt.-trial level |  | Both | Template | M | Process, Tech? | Short term pain in implementation. How will this be received by site? Impact on other stakeholders? Will it slow down study start up? Will I need new training materials? | Short term: streamlined protocol, less redundancy. Longer term: Easier site training, increased quality b/c of consistency, better site relations, More streamlined protocol development/writing | Reassurance that we have vetted this with stakeholders (sites, ERBs).
Study Mgmt.-country level |  | Both | Template | M | Process, Tech? | Short term pain in implementation. How will this be received by site? Impact on other stakeholders? Will it slow down study start up? Will I need new training materials? | Short term: streamlined protocol, less redundancy. Longer term: Easier site training, increased quality b/c of consistency, better site relations, More streamlined protocol development/writing | Reassurance that we have vetted this with stakeholders (sites, ERBs).
Data Mgmt.-eCRF Designers |  | Both | Template, endpoints, schedule of activities? Data Management Plan | H/M | Process, Tech | Schedule of activities (positive or negative change?) | Laying foundation for major technical improvements. Improved data quality b/c of site improvement. | Awareness, communication, continued alignment with CPT and DS workstreams. Traceability matrix.
Data Mgmt.-Database Designers |  | Both |  | H/M | Process, Tech |  | Laying foundation for major technical improvements. Improved data quality b/c of site improvement. | Awareness, communication, continued alignment with CPT and DS workstreams. Traceability matrix.
Statisticians |  | Internal | Template, standard endpoints | H | Process | minimal, move details to SAP | More consistency, streamlined, faster SAP | Awareness
Study Mgmt.-CRAs |  | Both | Template | M | People, process | If info is not in the protocol, where do I find it? | Longer term: less follow up with sites, high quality. For CROs - high level of consistency across companies | Awareness (they can be change agents)
PV |  | Internal | template, standardized wording | High | People, Process | Loss of control | More consistency, better compliance, training easier, shorter review time, | Communication, explanation, training, trust, HA input
Patient Safety Specialists |  | Internal
Reg Affairs |  | Internal | Loss of control around language | Low | People, process | global application | more consistency, harmonization | Communication, explanation, training, trust, HA input
Translational medicine |  | Internal | Loss of control around language
TA Leads/Product Owners |  | Internal | Loss of control around language | High | People, process, standards, organization | Depends on the level of granularity | quicker review times, investigator engagement | Communication, explanation, training, trust, Senior Management support
Standardization groups |  | Internal | Reduced workload |  | People, process, standards, organization | Need to align new template with existing sponsor standards | Reduced workload, broader use of standards, transparency | Communication, explanation, training,
Drug Supply Groups |  | Internal | template, standardized wording | M | Process, standards | loss of control, where should information now be housed? | Streamline this section , easier review | Communication, training on how to best use the language provided in the libraries
Training & Compliance Teams |  | Internal | Templates, SOPs, work instructions | H | Process, Standards | Template to be adapted to the Sponsor's style (font, etc), SOPs & work instructions to be revised | Once the template is rolled out there will be greater consistency across all TAs | Communication as the template is updated, training materials
Legally approved 8-Apr-2017